## Phase1 UAT 2026-09-21
Feature ID | Feature | Portal | Result | Observed during live test | Evidence / blocker
F01 | Portal login works for assigned user | Client | WORKING | Client credentials signed in successfully and loaded client workspace navigation. | Dashboard/Body Tracker/Check-ins/Progress Photos/Nutrition/Workout/Health Summary/Profile nav visible after sign-in.
F02 | Role-based access enforcement | Auth | WORKING | Client credentials were tested against Coach portal selection and denied. | UI message shown: 'This account cannot access the selected portal. Choose the portal assigned to your account.'
F03 | Password reset request flow | Auth + SMTP trigger | WORKING | Forgot-password request accepted for client email and cooldown started. | Status shown: reset link requested message + 'Resend in 59s'.
F04 | Client dashboard/workspace availability | Client | WORKING | Client dashboard loaded with role-specific cards and actions. | Client-only dashboard rendered with no coach/admin controls.
F05 | Body tracker (date + weight persistence flow) | Client | WORKING | Body Tracker accepted date + weight submission and completed save. | After save, status changed to 'Body progress saved to your XForm record.' and weight field reset.
F06 | Weekly check-ins (photos + measurements + ratings) | Client | WORKING | Check-ins page loaded full photo/measurement/rating workflow with submit control. | Pose selectors, weekly selectors, measurement fields, 1-5 and 1-10 ratings, text prompts, and submit button all present.
F07 | Nutrition workspace availability | Client | WORKING | Nutrition page opened with assigned meals and adherence actions. | Meal cards, macro totals, prep guides, and Followed/Partly/Missed actions rendered.
F08 | Workout workspace availability | Client | WORKING | Workout page opened successfully. | Page rendered expected pending-plan state plus performance-history section.
F09 | Health summary visibility | Client | WORKING | Health Summary opened with protected coach-approved summary sections. | Wellbeing signal/progress sentiment/health data/safety boundary sections rendered.
F10 | Client profile scope (phase-1 controls only) | Client | WORKING | Profile page showed goal/timezone/preferences controls only. | No target-weight or weekday controls present in the phase-1 client profile.
F11 | Coach portal login with provided credentials | Coach | WORKING | Provided coach email/password authenticated successfully. | Coach workspace loaded with Overview/Clients/Body Tracker/Nutrition/Workout/Libraries/Settings/Health/Audit Log.
F12 | Admin portal login with provided credentials | Admin | WORKING | Provided admin email/password authenticated successfully. | Admin portal loaded with team/roster controls.
F13 | Coach-led client enrollment + invite request | Coach | WORKING | Coach enrolled a new client and invite request completed. | Success banner shown: secure account-setup invitation sent; new client row appeared in roster.
F14 | Foundation intake pending visibility in coach roster | Coach | WORKING | Newly enrolled client showed pending intake state in roster and coach overview queue. | 'Intake pending' chip visible on client card; overview queue showed foundation intake pending signal.
F15 | Coach review and feedback loop (coach side) | Coach | WORKING | Coach review page loaded and accepted guidance + private-note saves. | Saved guidance persisted; private note appeared in the PRIVATE COACH NOTES section.
F16 | Coach libraries operations (food/exercise) | Coach | WORKING | Coach Libraries add-item flow completed for food entry. | New food item save succeeded and success message control appeared (dismiss message button).
F17 | Coach settings persistence | Coach | WORKING | Missing-weight threshold changed from 5 to 6, persisted after navigation, then restored to 5. | Save completed each time and persisted value was reloaded in settings.
F18 | CSV controls hidden in coach UX (phase-1 scope protection) | Coach | WORKING | Clients and Settings pages did not expose CSV preview/import/export controls. | No CSV preview button in Clients; Settings nav only shows 'System setup' and 'Security' (no 'Data tools').
F19 | Admin team snapshot counts | Admin | WORKING | Admin team snapshot loaded with roster and status filter controls. | Total coaches/active/offboarded/total clients summary cards and roster filter rendered.
F20 | Admin enroll/reset/offboard workflows | Admin | PARTIAL | Enroll, password reset, and offboard actions executed in admin UI. | Enroll and offboard completed. Password reset generated new credentials but displayed warning: audit entry could not be recorded.
F21 | Admin privacy-limited assignment visibility | Admin | WORKING | Admin coach-detail panel explicitly displayed privacy-limited assignment model. | UI text states only client codes/assignment dates are shared and personal health details remain private.
F22 | Durable photo cleanup retry worker behavior | Backend service | NOT TESTABLE FROM PORTAL | Feature is backend worker + queue behavior, not directly observable through portal UI alone. | Needs logs/DB/R2 or backend harness evidence.
F23 | SMTP mailbox acceptance (invite email receipt + password set + fresh login) | Auth + SMTP | PARTIAL | Invite/reset request flows are functioning from portal UI. | Recipient inbox receipt, link completion, and fresh-login completion were not independently validated in this run.
F24 | Phase-1 live test conclusion | All portals | PARTIAL | Most phase-1 portal features are now working across Client/Coach/Admin. | Open items: F20 audit-log warning during reset workflow and F23 mailbox acceptance proof pending; F22 requires backend evidence.